## RACI
RACI for Technology Projects
| Client Lead | Project Sponsors | IT PMO | IT Lead
Project Initiation and Administration
Register the Project with IT (TAP) | R | I | I | A
Create Project Charter | A/R | C | I | C
Identify Risks, Dependencies | A | I | I/C | R
Review SDLC Process Documentation | R | I | I/C | A
Develop a Change Management and Communications Strategy | A/R | C | I | C
Planning /Requirements Gathering
Develop Detailed Business Requirements | A/R | C | I | C
Obtain Approval of System Design and Solution Architecture | A | I | I | R | * A moved to Client as they are accountable for the ultimate success of the design, reporting to their sponsor. Responsibility lies with EA to create approve the design.
Obtain Approval on System Design and Solution Architecture | A | I | I | R
Financial Management
Requests/obtain funding via governance committee | R | A | C | C
Conduct Appropriation Process | R | A | I | C
Forecast and Cashflow | R | C | I | A
Capture IT O&M Costs and/or Benefits | R | I | C | A
Track and Monitor Financials | R | I | C/R | A
Resource Management and Procurement
Plan and Budget for Implementation & Support (Labor) | R | C | I | A
Purchasing or Acquisition of Materials and/or Services | R | C/R | C | A
Schedule Management
Create Project Schedules with IT Tasks/Milestones and Update Regularly | R | I | I/C | A
Create and Track Milestone Dependencies between Projects | R | I | I/C | A
Track and Monitor Project Schedule | R | I | C/R | A
Testing
Manage Unit, Integration and System, Performance Testing | C | I | I | A/R
Develop Test Cases | A/R | I | I | C
Perform UAT | A/R | I | I | C
Deployment & Post-Production Support
Obtain Change Advisory Board (CAB) or Technical Review Board (TRB) Approval* | C | I | I | A/R
Complete Production Acceptance Checklist | A | I | I/C | R
Transition to Run Team | C | I | I | A/R
Rate Case
Create Whitepaper | A/R | C | I/C | C
Rate Case Sponsorship | R | A | I | C
* CAB handles high/critical changes, TRB
Useful Links:
PI360 - http://pi360/pwa
IT PMO SP Site for registration - http://ceteams/SiteDirectory/SDG/Project%20Registration/Forms/AllItems.aspx
IT Library - http://ceintranet/InformationResources/IR%20Project%20Library/Pages/default.aspx

## Elements in CI-215
Items in current CI-215
Sponsoring Org
Vision and Scope |  | Joint
Business Case, Detailed Business Requirements |  | Sponsor
Benefits |  | Joint
Rate Case documentation |  | Joint
Requests and obtains approval for funding via governance committee |  | Joint
TAP registration |  | Joint
Assigns business sponsor and PM
Prepares and executes UAT test plan |  | Sponsor
change management initiatives |  | Joint
Verifies system meets scope/business req |  | Sponsor
Ensures adequate resources are in place and budgeted for implementation and post-prod support |  | Joint
Manages change requests and system upgrades |  | IT
compliance with software license agreements |  | Joint
compliance with Company financial management procedures |  | Joint
procurement of materials and services |  | Joint
Business Sponsor | -> Project Sponsor
Coordinates the above for sponsoring org |  | N/A
May assign addt'l resources from business org as needed |  | N/A
Sponsoring PM
manage process doc | Clarify: Process doc? | Joint
securing approvals |  | Joint
project plan |  | Joint
managing artifacts (issues/schedule/cost) |  | Joint
comms to stakeholders |  | Joint
IT
final technology selection |  | IT
detailed system design |  | IT
system development |  | N/A?
testing: unit testing, integration and system testing, performance testing |  | N/A?

## Questions
Questions to ask
1) Under ITB governance, while in-flight projects are to continue to be funded within their organization's budget, new projects are to be budgeted and appropriated within IT. Does this blur the lines between categories "IT Managed," "Client Managed" and "IT & Client Managed"? Is there a better set of categories by which to sort IT projects?
2) Should we be setting clearer expectations between capital and O&M projects?
3) Do we still agree with the division of responsibilities as laid out by the current CI-215, or have they shifted since time of writing?
4) Vertical subcategories: Is 4 too many or too few? (IT PMO, Sponsoring lead, IT lead, leadership) Are they the right categories?
5) Are there any elements of project initiation or implementation missing from the list entirely?
6) Are the responsibilities different enough between in-house development and vendor-lead projects that we should be differentiating here?
7) Is the granularity of tasks within the RACI appropriate? Is there opportunity to reduce or combine?
Do we list everything from the SDLC? Everything in the playbook?

## Definitions
Why RACI: RACI is useful in clarifying roles and responsibilities in cross-functional projects and processes. RACI is an acronym derived from the four key responsibilities most typically used: Responsible, Accountable, Consulted, and Informed.
R = Responsible: The person who performs the work. People or stakeholders who are the "doers" of the work. They must complete the task or objective or make the decision. Several people can be jointly Responsible.
A = Accountable/Approver: The person ultimately accountable for the work or decision being made. Person or stakeholder who is the "owner" of the work. He or she must sign off or approve when the task, objective or decision is complete. This person must make sure that responsibilities are assigned in the matrix for all related activities. Success requires that there is only one person Accountable, which means that "the buck stops there.
C = Consulted/Contributor: Anyone who must be consulted with prior to a decision being made and/or the task being completed. People or stakeholders who need to give input before the work can be done and signed-off on. These people are "in the loop" and active participants.
I = Informed: Anyone who must be informed when a decision is made or work is completed. People or stakeholders who need to be kept "in the picture." They need updates on progress or decisions, but they do not need to be formally consulted, nor do they contribute directly to the task or decision.